## Slide 1
Water for Schools
Detailed Project Plan, Costing & Timeline
Prepared for business, corporate and institutional funding partners
Simunye Satya Bharat Foundation (SSBF) · SSB Foundation NPC · Reg No. 2024/542394/08

## Slide 2
WHO WE ARE
Simunye Satya Bharat Foundation
SSBF is a Phoenix-born, Durban-based non-profit company (SSB Foundation NPC, Reg No. 2024/542394/08) built on the belief that communities rise fastest when they take responsibility for their own future. We start with water at schools — because without water there is no learning.
This deck sets out the full plan for Phase 1 — Water for Schools — including technical specification, itemised costing, roll-out timeline and how funding partners can get involved.
🎯
Mission
Restore water security and continuity of learning to Phoenix schools.
🌅
Vision
A Phoenix that funds and manages its own upliftment, school by school.
🤝
Approach
Direct school partnerships, backed by corporate & community funding.
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
2

## Slide 3
THE PROBLEM
A water crisis that has become an education crisis
14–16 hrs
daily water cuts
50–60%
water lost to leaks
15–30
teaching days lost / yr
81%
Gr.4 learners can't read for meaning (PIRLS, national)
What schools lose when the taps run dry
• Early dismissals when toilets and handwashing stations become unusable
• Heat exhaustion & dehydration risk, with bottled water unaffordable for most families
• Girls missing school entirely without private, functioning sanitation
• Science and biology practicals abandoned — no water for experiments or safety showers
• Foundational literacy and numeracy gains eroded by lost, uninterrupted teaching time
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
3

## Slide 4
THE SOLUTION
Engineering a system that meets real school demand
For a school of ~500 learners with roughly 48 toilets, 36 basins and 6 outdoor taps, peak break-time demand reaches 150–250 L/min. A standard household (peripheral) pump maxes out at 35–40 L/min and stalls under this load — a multi-stage centrifugal pump is required.
🛢️
Storage
2× 5,000L tanks in series on a concrete base (7,500–10,000L). Scalable to 15,000–20,000L for larger schools.
⚙️
Pump
1.5–2.2kW multi-stage centrifugal pump — delivers 200+ L/min while maintaining steady pressure.
🎛️
Controller
VSD / electronic pressure controller — scales output automatically, protecting the pump motor from rapid cycling.
Storage Tanks → Multi-Stage Pump → VSD / Pressure Controller → School Water Mains
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
4

## Slide 5
INVESTMENT
Core System — Itemised Cost
Component
Estimated Cost
Water / JoJo-type Tank (5,000L) × 2
R12,000
Pump (2.2kW) with Controller
R8,000
Pump Controller (backup/alternative)
R500
Ball Flat Valve × 2
R1,000
Concrete Base (2m × 4m)
R5,000
Rubber Base Mat (2m × 4m)
R1,500
Piping & Fittings
R5,000
Pump Cover
R1,000
Sub-total (materials)
R34,000
Labour
R10,000
TOTAL (per school)
R44,000
Rounded Budget Figure
R50,000
per school, all-inclusive of materials and labour
Also available:
10,000L single tank option — approx. R14,799 (for larger schools, can combine with 5,000L units for 15,000–20,000L capacity).
All figures are current supplier estimates and may vary at time of purchase.
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
5

## Slide 6
OPTIONAL ENHANCEMENTS
Extending the Core System
🔒
Security Cage
Fencing / poles
R8,000
Awning
R4,000
Locks
R1,000
Labour
R2,000
SUB-TOTAL
R15,000
🌧️
Rainwater Harvesting
Tanks (2×5,000L / 4×2,500L)
R12,000
Base × 2
R6,000
Pump 2.2kW + controller
R16,000
Plumbing + Labour
R20,000
SUB-TOTAL
R54,000
🚰
Water Filtration (×2 outlets)
Filter systems × 2
R10,000
Plumbing
R2,000
Labour
R4,000
SUB-TOTAL
R16,000
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
6

## Slide 7
FUNDING OPPORTUNITY
Sponsorship Tiers
1 School
R50,000
Fully fund one school's backup water system.
5 Schools
R250,000
A corporate-level commitment across five schools, with branding at each.
10 Schools
R500,000
For major business & international funding partners.
Sponsors are listed on the SSBF website and receive on-site branding at every school they fund. In-kind sponsorship of materials (tanks, pumps, piping) is also welcomed.
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
7

## Slide 8
ROLL-OUT PLAN
Indicative Timeline — First School Cohort
Month 1
Engagement
Meet principals, present the project, confirm points of contact.
Month 2
Agreements & Funding
Sign MOUs; finalise sponsor / donor commitments per school.
Month 3
Procurement
Order tanks, pumps, controllers & materials; schedule installation.
Month 4
Installation
Install and pressure-test systems; sponsor branding placed.
Month 5+
Handover & Review
Handover to school; quarterly maintenance check-ins begin.
Timeline assumes committed funding is in place by the end of Month 2 for the school cohort in question. Multiple cohorts can run in parallel as funding allows.
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
8

## Slide 9
FUNDING STRATEGY
How Phase 1 Will Be Funded
🏢
Corporate & Business
Major retailers, banks, insurers, manufacturers and businesses operating in or serving Phoenix.
🌍
International Funding
Global foundations, tech companies and development funders supporting education & WASH initiatives.
🧰
Materials & Trade Sponsors
Tank, pump and hardware manufacturers, wholesalers and retailers — cash or in-kind.
📣
Community & Media
Individual donors, community fundraising, and media partners donating advertising space.
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
9

## Slide 10
LOOKING AHEAD
Water for Schools is Phase 1 of 7
1
Water for Schools
2
Solar for Schools
3
Fix Our Schools
4
Community Upliftment
5
Secure Our Community
6
Funding Our Projects
7
Web 4 Education
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
10

## Slide 11
Partner With Us
Every school we secure means teaching days protected, dignity restored, and a stronger foundation for the next generation of Phoenix.
info@simunyesatya.org
+27 83 799 3490 (WhatsApp / Call)
The Centenary, 30 Meridian Drive, Umhlanga, 4319 (by appointment)
simunyesatya.org
Simunye Satya Bharat Foundation · Water for Schools · Detailed Plan & Costing
11